## Sheet1
CLUE WG milestones/deadlines
Document/deliverable: | WG doc | Pre-WGLC | WGLC | EDR | To IESG | Approved | Lead Author(s) | Shepherd | Comments
draft-ietf-clue-telepresence-use-cases/ | Done | N/A | Done | N/A | Done (Sept. 2013) | RFC 7205 | Roni Even | Mary Barnes
draft-ietf-clue-telepresence-requirements | Done | N/A | Done | N/A | Done (Nov 2013) | RFC 7262 | Mary Barnes | Paul Kyzivat
draft-ietf-clue-framework/ | Done | 2013-06-20 | 2014-07-31 | 2014-07-31 | 2014-09-30 |  | Mark Duckworth | Mary Barnes | Waiting for other docs before progressing
draft-ietf-clue-data-model-schema | Done | 2014-07-04 | 2014-08-30 | 2014-08-30 | 2014-11-30 |  | Roberta Presta/Simon Romano | Mary Barnes
draft-presta-clue-protocol/ | 2014-06-10 | 2014-08-15 | 2014-09-30 | 2014-09-30 | 2014-11-30 |  | Roberta Presta/Simon Romano | Mary Barnes
draft-ietf-clue-datachannel | Done | 2014-08-31 | 2014-09-30 | 2014-09-30 | 2014-11-30 |  | Christer Holmberg | Paul Kyzivat
draft-ietf-clue-rtp-mapping/ | Done | 2014-09-30 | 2014-11-30 | 2014-11-30 | 2015-01-31 |  | Roni Even/Jonathan Lennox | Paul Kyzivat
draft-ietf-clue-signaling/ | Done | 2014-10-31 | 2014-12-31 | 2014-12-31 | 2015-02-28 |  | Rob Hansen | Mary Barnes
CLUE Call Flows | 2014-07-31 | 2014-10-31 | 2014-12-31 | 2014-12-31 | 2015-02-28 |  | Roni Even/Rob Hansen | Paul Kyzivat
EDR = Early Directorate Review