## Sheet1
CLUE WG milestones/deadlines
Document/deliverable: | WG doc | Pre-WGLC | WGLC | EDR | To IESG | Approved | Author(s) | Shepherd | Comments
draft-ietf-clue-telepresence-use-cases/ | Done | N/A | Done | N/A | Done (Sept. 2013) |  | Roni Even | Mary Barnes
draft-ietf-clue-telepresence-requirements | Done | N/A | Done | N/A | 2013-11-30 |  | Mary Barnes | Paul Kyzivat
draft-ietf-clue-framework/ | Done | 2013-11-30 | 2014-02-28 | 2014-02-28 | 2014-08-31 |  | Mark Duckworth | Mary Barnes | Waiting for other docs before progressing
draft-ietf-clue-data-model-schema | Done | 2013-12-31 | 2014-02-28 | 2014-03-31 | 2014-08-31 |  | Roberta Presta/Simon Romano | Mary Barnes
draft-presta-clue-protocol/ | 2013-12-31 | 2014-03-31 | 2014-05-30 | 2014-05-30 | 2014-09-30 |  | Roberta Presta/Simon Romano | Mary Barnes
CLUE Data Channel | 2014-03-31 | 2014-05-30 | 2014-07-31 | 2014-07-31 | 2014-09-30 |  | Christer Holmberg (?) | Paul Kyzivat
draft-ietf-clue-rtp-mapping/ | Done | 2014-06-30 | 2014-08-31 | 2014-08-31 | 2014-10-31 |  | Roni Even/Jonathan Lennox | Paul Kyzivat
draft-kyzivat-clue-signaling/ | 2013-12-31 | 2014-07-31 | 2014-09-30 | 2014-09-30 | 2014-11-30 |  | Rob Hansen/Paul Kyzivat | Mary Barnes
CLUE Call Flows | 2014-04-30 | 2014-09-30 | 2014-11-30 | 2014-11-30 | 2015-01-31 |  | Lorenzo Miniero | Paul Kyzivat
EDR = Early Directorate Review