## milestones-deadlines
CLUE WG milestones/deadlines |  | Pre-WGLC |  | WGLC |  | Early Directorate Review
Document/deliverable: | WG doc | Start | duration | Start | duration | What? | Start | duration | To IESG | Approved | Lead Author(s) | Shepherd | Comments
draft-ietf-clue-telepresence-use-cases/ | Done | N/A |  | Done |  | N/A |  |  | Done (Sept. 2013) | RFC 7205 | Roni Even | Mary Barnes
draft-ietf-clue-telepresence-requirements | Done | N/A |  | Done |  | N/A |  |  | Done (Nov 2013) | RFC 7262 | Mary Barnes | Paul Kyzivat
draft-ietf-clue-framework/ | Done | Done |  | 2015-01-19 | 2 wks | security | 2014-12-08 | 4 wks | 2015-03-30 |  | Mark Duckworth | Mary Barnes | Waiting for other docs before progressing
draft-ietf-clue-data-model-schema | Done | Done |  | 2015-02-02 | 2 wks | security, xml | 26-Jan-15 5-Jan-15 | 3 wks 3 wks | 2015-03-30 |  | Roberta Presta/Simon Romano | Mary Barnes
draft-ietf-clue-protocol | Done | 2015-01-05 | 2 wks | 2015-02-16 | 2 wks | security, xml | 26-Jan-15 5-Jan-15 | 3 wks 3 wks | 2015-03-30 |  | Roberta Presta/Simon Romano | Mary Barnes
draft-ietf-clue-datachannel | Done | 2015-01-19 | 2 wks | 2015-03-02 | 2 wks | - |  |  | 2015-03-30 |  | Christer Holmberg | Paul Kyzivat
draft-ietf-clue-rtp-mapping/ | Done | 2015-02-02 | 2 wks | 2015-03-02 | 2 wks | - |  |  | 2015-03-30 |  | Roni Even/Jonathan Lennox | Paul Kyzivat
draft-ietf-clue-signaling/ | Done | 2014-11-17 | 4 wks | 2015-03-02 | 2 wks | security | 2015-01-05 | 3 wks | 2015-03-30 |  | Rob Hansen | Mary Barnes
CLUE Call Flows | TBD | ? |  | ? |  |  | ? |  | ? |  | Roni Even/Rob Hansen | Paul Kyzivat

## timeline
2014-11-10 | 2014-11-17 | 2014-11-24 | 2014-12-01 | 2014-12-08 | 2014-12-15 | 2014-12-22 | 2014-12-29 | 2015-01-05 | 2015-01-12 | 2015-01-19 | 2015-01-26 | 2015-02-02 | 2015-02-09 | 2015-02-16 | 2015-02-23 | 2015-03-02 | 2015-03-09 | 2015-03-16 | 2015-03-23 | 2015-03-30 | 2015-04-06
ietf91 |  | thanksgiving |  |  |  | xmas | new years | [11 empty] | ietf92
| signaling pre-wglc | [6 empty] | protocol pre-wglc |  | data-channel pre-wglc |  | rtp pre-wglc | [7 empty] | framework iesg
[10 empty] | framework wglc |  | data-model wglc |  | protocol wglc |  | signaling wglc |  |  |  | signaling iesg
[16 empty] | data-channel wglc |  |  |  | data-model iesg
[16 empty] | rtp wglc |  |  |  | protocol iesg
|  |  |  | framework sec review |  |  |  | signaling sec review |  |  | protocol sec review | [8 empty] | rtp iesg
[11 empty] | data-model sec review | [8 empty] | data-channel iesg
protocol xml review
data-model xml review